## Sprint1
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 90 | 162 | 157 | 152 | 130 | 115 | 99 | 90 | 78 | 60 | 47 | 30
Architecture diagram | Architecture diagram | Varun/Shivani | 10 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 0
DB design | DB design | Sakshi/Varun | 12 | 0 | 0 | 1 | 3 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0
Frontend baseline | Frontend baseline | Raj | 20 | 0 | 0 | 8 | 0 | 3 | 0 | 1 | 0 | 0 | 2 | 3 | 0 | 3 | 0
Backend baseline | Backend baseline | Varun | 20 | 0 | 0 | 4 | 3 | 0 | 0 | 3 | 4 | 4 | 3 | 0 | 0 | 0 | 0
Wireframe for login, registration, landing and listing | Wireframe for login, registration, landing and listing | Shivani | 12 | 0 | 0 | 0 | 1 | 4 | 0 | 2 | 2 | 0 | 1 | 2 | 0 | 0 | 0
Unit Testing Framework | Unit Testing Framework | Sakshi | 6 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
UI routing protection added | UI routing protection added | Raj | 10 | 0 | 0 | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 2 | 1 | 0 | 0 | 0
|  |  | Total | 90 | 90 | 73 | 63 | 52 | 48 | 42 | 30 | 23 | 12 | 2 | -15 | -27 | -34
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
Team:
Varun | 9 hours / Week
Sakshi | 9 hours / Week
Raj | 9 hours / Week
Shivani | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint2
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-03-12 | ##### | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 72 | 68 | 62 | 54 | 47 | 41 | 38 | 35 | 32 | 27.5 | 19
hotel search component | hotel search component | Varun | 8 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 2 | 1.5 | 1 | 0 | 0 | 0
Backend baseline | Backend baseline | Varun | 12 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0
User Registration | User Registration | Raj | 10 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | 0
Wireframe Hotel Booking and booking summary UI | Wireframe Hotel Booking and booking summary UI | Shivani | 6 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Backend service for listing locations | Backend service for listing locations | Sakshi | 8 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0
Backend for Default hotel listing Api | Backend for Default hotel listing Api | Sakshi | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0
Backend for Hotel details Api | Backend for Hotel details Api | Varun | 6 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
Hotel Listing UI | Hotel Listing UI | Shivani | 10 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0
Backend for Login and Registration | Backend for Login and Registration | Raj | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0
|  |  | Total | 68 | 62 | 54 | 47 | 41 | 38 | 35 | 32 | 27 | 19 | 11 | 8 | 2 | 0
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
72
Team:
Varun | 9 hours / Week
Sakshi | 9 hours / Week
Raj | 9 hours / Week
Shivani | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint3
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-03-26 | ##### | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 72 | 66 | 52 | 34 | 23 | 19 | 11 | 5 | -5 | -12 | -30 | 8 | 5 | 5
Backend service for Booking component | Backend service for Booking component | Sakshi |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0
Booking summary frontend | Booking summary frontend | Shivani |  | 3 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 0
My Bookings Change/ Cancel Booking Wireframes | My Bookings Change/ Cancel Booking Wireframes | Shivani |  | 0 | 2 | 0 | 2 | 0 | 4 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0
Bookings api | Bookings api | Sakshi |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0
Ec2 autoscaling group | Ec2 autoscaling group | varun |  | 0 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0
pricing strategy schema and api | pricing strategy schema and api | Varun/Sakshi |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0
Amenities listing api | Amenities listing api | Sakshi |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
Code Refactoration | Code Refactoration | Raj |  | 2 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 1
Persistance for JWT | Redux Persistance Introduced | Raj |  | 1 | 0 | 2 | 1 | 0 | 1 | 1 | 2 | 0 | 2 | 0 | 0 | 1 | 0
Frontend Integration - Sprint 1 | Frontend Integration - Sprint 1 | Raj |  | 1 | 0 | 2 | 2 | 0 | 0 | 1 | 2 | 1 | 2 | 0 | 1 | 2 | 2
Route Protection Authentication | Introduced AWS Cognito to the System | Raj |  | 0 | 0 | 3 | 1 | 2 | 0 | 2 | 1 | 1 | 2 | 1 | 1 | 0 | 0
UML Diagrams | UML Diagrams | Shivani |  | 0 | 2 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 3 | 3 | 0 | 0 | 2
|  |  | Total | 65 | 53 | 34 | 23 | 19 | 11 | 5 | -5 | -12 | -30 | -41 | -49 | -54 | -59
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
0
Team:
Varun | 9 hours / Week
Sakshi | 9 hours / Week
Raj | 9 hours / Week
Shivani | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint4
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-04-09 | ##### | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 72 | 64 | 57 | 42 | 32 | 23 | 20 | 16 | 10 | 3 | -4
Jenkins integration | Jenkins integration | Varun |  | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0
Pricing Strategy | Pricing Strategy | Varun |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
create a hotel, location, add rooms Api | create a hotel, location, add rooms Api | Sakshi |  | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
backend services for creation (hotel, location, room) UI | backend services for creation (hotel, location, room) UI | Shivani |  | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0
My Bookings Change | My Bookings Change | Shivani |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
My Bookings Change | My Bookings Change | Shivani |  | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
My Booking Cancel Api | My Booking Cancel Api | Sakshi |  | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0
Frontend Integration - Sprint - 2 | Frontend Integration - Sprint - 2 | Raj/Shivani |  | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 2
Admin | Admin | Raj |  | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 2 | 1 | 2 | 0 | 1 | 0 | 0
Backend Route Protection | Backend Route Protection | Raj |  | 2 | 0 | 1 | 2 | 1 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 0
DB User | DB User | Varun |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 64 | 57 | 42 | 32 | 23 | 20 | 16 | 10 | 3 | -4 | -11 | -16 | -20 | -23
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
0
Team:
Varun | 9 hours / Week
Sakshi | 9 hours / Week
Raj | 9 hours / Week
Shivani | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint5
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-04-23 | ##### | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 72 | 63 | 54 | 46 | 39 | 35 | 31 | 27 | 18 | 7 | 0
Booking Summary UI changes and integration | Booking Summary UI changes and integration | Varun/Shivani |  | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0
MyBooking Cancelation integration | MyBooking Cancelation integration | Shivani |  | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Room Availability API | Room Availability API | Varun/Sakshi |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
Booking Cancel Booking Wireframes | Booking Cancel Booking Wireframes | Shivani |  | 0 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Booking Cancel Booking UI | Booking Cancel Booking UI | Shivani |  | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 3 | 1 | 1 | 0 | 0 | 0 | 0
Booking Cancel API | Booking Cancel API | Sakshi |  | 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0
Admin Role API | Admin Role API | Sakshi |  | 1 | 1.5 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0
Customers List API | Customers List API | Varun |  | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Redux Persistance | Improved Redux Persistance | Raj |  | 1 | 0 | 2 | 1 | 0 | 0 | 2 | 1 | 1 | 0 | 2 | 1 | 2 | 0
Front End Integration | Front End Integration | Raj |  | 1 | 0 | 2 | 1 | 0 | 2 | 0 | 1 | 3 | 0 | 1 | 1 | 1 | 2
|  |  | Total | 63 | 54 | 46 | 39 | 35 | 31 | 27 | 18 | 7 | 0 | -5 | -2 | -5 | -7
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
0
Team:
Varun | 9 hours / Week
Sakshi | 9 hours / Week
Raj | 9 hours / Week
Shivani | 9 hours / Week
Total Available Hours During Sprint: | 72